## Prod runs (hidden)
| Final Processing | Place on Hold | Notes
AE.IPRI109 - PBI Death Verification Extract | Daily at 3:55:39am. | 2025-07-10 08:00 | Or put them all on hold at 6 PM
AE.PERS_REFRESH - Personal Data Refresh | Daily at 3:55:39am. | 2025-07-10 08:00
AE.IPRI103 - INPAS Calculation Deletion | Daily at 2:00:00am. | 2025-07-10 08:00
AE.SCRTY_OPRCLS - Security Refresh | Daily at 8:00:00pm. | 2025-07-10 08:00
AE.IPR_WL_TIMEOUT - Worklist Timeout Processing | Daily at 7:50:00pm. | 2025-07-10 18:00
AE.IPRI007 - PreNote Process | Every Monday at 8pm. | 2025-07-10 18:00
AE.IPRM031 - Periodic Filenet polling program | every 15 minutes from 7am-7pm(including a 7pm run) | 2025-07-10 18:00

## SJC Detailed Upgrade Steps (hidden)
# | Upgrade Task | Duration | Start | End | Status | Notes | Owner
Refresh Oracle FSCMDEV with Copy of FSCMPRD
Pre | Drop Database FSCMDEV | 8 hours | 9:37am |  | Not Started | (Add to Pre Upgrade Tasks) This can be done the night before and normally takes around 8 hours | Jeff | x
Pre | Create Folder Structure in Prod | 30 min |  |  | Not Started | Sync up FINPRD | Jeff | x
1 | Copy Prod Files | 1 hour |  |  | Not Started | Database files | Jeff | x
2 | Import | 4 hours |  |  | Not Started |  | Jeff | x
3 | Post Refresh Tasks | 30 min |  |  | Not Started |  | Jeff | x
4 | Cleanup Audits | 1 hours |  |  | Not Started |  | Jeff | x

## Early Preparation
SDCOE PeopleTools Upgrade 8.62.10 Go Live | Complete on | Status | Lead | Team | Comments
Weeks prior to Go Live (Go Live on Fri 09/25 - Sun 09/27)
Finalize Validation cycles - who will test and when |  |  | SDCOE Team
Provide List of IT User id's & Business user id's to unlock for Validation(s) |  |  | SDCOE Team | SDCOE Team
Provide pre-upgrade SYSAUDIT & DDDAUDIT reports for Review |  |  | Sribalaje | Sribalaje, Ganesh
Ensure the issues reported by the customer and during the upgrade are reviewed |  |  | Sribalaje | Sribalaje, Ganesh
Confirm list of Retrofit projects and batch objects if any |  |  | Steve | SDCOE Team
Code Freeze in Prod |  |  | Steve | SDCOE Team
Create blackout request on the Production System for CRT | 2026-09-24
COMM: Prepare for F5 redirect configuration change. Notify CRT Network Team of Go Live weekend | 2026-09-23 |  | Sribalaje | Nirmal/Bhuvan | Email to Sandeep and F5 Team
COMM: Notify Windows/Linux/Network Team to be available In case of any issues | 2026-09-23 |  | Sribalaje | Bhuvan/Digvijay
COMM: Notify SDCOE users of weekend down time. Logistics for weekend validation | 2026-09-23
Peopletools Components & Domain Creation on Production
Install Peoplesoft components (PT8.62.10) on the Prod servers(App/Web/Process scheduler servers) | 2026-09-18 |  | Sribalaje | Sribalaje, Ganesh
Create and configure Application servers & Process scheduler Servers(Including PSNT) | 2026-09-18 |  | Sribalaje | Sribalaje, Ganesh
Create and configure Webservers on Internal & DMZ(ESS, Supplier Portal, CG) | 2026-09-18 |  | Sribalaje | Sribalaje, Ganesh
Ensure Customizations are applied on all webservers | 2026-09-18 |  | Sribalaje | Sribalaje, Ganesh
Install and configure OpenSearch & Kibana(Insights) | 2026-09-18 |  | Sribalaje | Sribalaje, Ganesh
Configure X-Forwarding setup on all Webserver console | 2026-09-18 |  | Sribalaje | Sribalaje, Ganesh
Ensure system-temp directory is copied from old PS_HOME | 2026-09-18 |  | Sribalaje | Sribalaje, Ganesh

## Go_Live_Plan
| SDCOE PeopleTools Upgrade 8.62.10 Go Live | Dur HR:MM | Start | End | Status | Lead | Team | Notes
| Production Control before Upgrade Activities |  | 2026-09-25 12:00 | 2026-09-25 03:15
| COMM: Production coming down at 6:00. Do Not Kick-Off Long Running Processes after 3:00 PM | 0:00 | 2026-09-25 12:00 | 2026-04-17 12:00 |  |  | SDCOE Team
1 | Hold the db refresh schedule for U & X until Go Live | 0:10 | 2026-09-25 12:00 | 2026-09-25 12:10 |  | Sergey | Prakash/Ravi
2 | Disable Scheduled backups of Production | 1:00 | 2026-09-25 12:00 | 2026-09-25 13:00 |  | Sergey | Prakash/Ravi
3 | Disable cron jobs from all Linux servers | 0:10 | 2026-09-25 12:00 | 2026-09-25 12:10 |  | Sribalaje | Sribalaje, Ganesh
4 | Perform complete Pre-IVT on SDHP92, SDFP92 & SDPP91 | 1:30 | 2026-09-25 12:00 | 2026-09-25 13:30 |  | Sribalaje | Sribalaje, Ganesh
5 | COMM: Complete work by 6:00 Start of Upgrade Go Live | 0:00 | 2026-09-25 15:00 | 2026-09-25 15:00 |  |  | SDCOE Team
6 | Hold all the scheduled jobs | 0:15 | 2026-09-25 03:00 | 2026-09-25 03:15 |  | Doug | Doug
| PeopleTools Upgrade PT 8.62.10 |  | 2026-09-25 18:00 | 2026-09-26 03:40
7 | COMM: System is down. Start of Upgrade Go Live | 0:00 | 2026-09-25 18:00 | 2026-09-25 18:00 |  |  | SDCOE Team
8 | Confirm all Production processing is complete. No running processes. | 0:10 | 2026-09-25 18:00 | 2026-09-25 18:10 |  |  | SDCOE Team
9 | Bring down all Webserver/Application servers & Elastic Search/Kibana | 0:20 | 2026-09-25 18:10 | 2026-09-25 18:30 |  | Sribalaje | Sribalaje, Ganesh
10 | Create Production DB restore point Before PT8.62 Upgrade-(Flashback and Incremental) | 0:30 | 2026-09-25 18:30 | 2026-09-25 19:00 |  | Sergey | Prakash/Ravi
11 | Lock all users except System users(Customer needs to provide user lists for excluding) | 0:20 | 2026-09-25 19:00 | 2026-09-25 19:20 |  | Sribalaje | Sribalaje, Ganesh | See Lockout_Scripts tab
12 | Prechecks for upgrade on CA | 0:20 | 2026-09-25 19:20 | 2026-09-25 19:40 |  | Sribalaje | Sribalaje, Ganesh
13 | Configure, Validate Change Assistant and load PT upgrade job. | 0:30 | 2026-09-25 19:40 | 2026-09-25 20:10 |  | Sribalaje | Sribalaje, Ganesh
14 | Update statistics | 0:15 | 2026-09-25 20:10 | 2026-09-25 20:25 |  | Sribalaje | Sribalaje, Ganesh
15 | Perform Initial Alter audit | 1:00 | 2026-09-25 20:25 | 2026-09-25 21:25 |  | Sribalaje | Sribalaje, Ganesh
16 | Updating PeopleTools system tables | 0:30 | 2026-09-25 21:25 | 2026-09-25 21:55 |  | Sribalaje | Sribalaje, Ganesh
17 | Compare report of Records, Fields & Indexes | 0:30 | 2026-09-25 21:55 | 2026-09-25 22:25 |  | Sribalaje | Sribalaje, Ganesh
18 | Copying Select Objects from the PPLTLS84CUR Project | 0:30 | 2026-09-25 22:25 | 2026-09-25 22:55 |  | Sribalaje | Sribalaje, Ganesh
19 | Compare of objects other than Records, Fields & Indexes | 1:00 | 2026-09-25 22:55 | 2026-09-25 23:55 |  | Sribalaje | Sribalaje, Ganesh
20 | Copying the PPLTLS84CUR Project other than Records, Fields & Indexes | 0:45 | 2026-09-25 23:55 | 2026-09-26 00:40 |  | Sribalaje | Sribalaje, Ganesh
21 | Loading PeopleTools data | 0:30 | 2026-09-26 00:40 | 2026-09-26 01:10 |  | Sribalaje | Sribalaje, Ganesh
22 | Perform PeopleTools data conversion | 0:30 | 2026-09-26 01:10 | 2026-09-26 01:40 |  | Sribalaje | Sribalaje, Ganesh
23 | Creating Updated Peopletools views | 0:30 | 2026-09-26 01:40 | 2026-09-26 02:10 |  | Sribalaje | Sribalaje, Ganesh
24 | Running the final Audit reports | 1:30 | 2026-09-26 02:10 | 2026-09-26 03:40 |  | Sribalaje | Sribalaje, Ganesh
25 | Create Production DB restore point after PeopleTools Upgrade | 0:20 | 2026-09-26 03:40 | 2026-09-26 04:00 |  | Sergey | Prakash/Ravi
26 | COMM: Provide update to Core Team Go Live string. PT8.62 upgrade complete | 0:00 | 2026-09-26 04:00 | 2026-09-26 04:00 |  | Sribalaje | Sribalaje, Ganesh
| Post Upgrade Activities |  | 2026-09-26 04:00 | 2026-09-26 04:00
27 | F5 Configuration changes | 0:25 | 2026-09-26 04:00 | 2026-09-26 04:25 |  | Nirmal | Bhuvan | F5 team
28 | Bring up all Web/App & Process scheduler servers and OpenSearch/Insights | 1:00 | 2026-09-26 04:25 | 2026-09-26 05:25 |  | Sribalaje | Sribalaje, Ganesh
29 | Recompile Cobols on HCM & FSCM | 0:15 | 2026-09-26 05:25 | 2026-09-26 05:40 |  | Sribalaje | Sribalaje, Ganesh
30 | Ensure DisableOrigin is removed on all webprofiles(HCM,FSCM,Portal,Esupplier, CG.ESS) | 0:20 | 2026-09-26 05:40 | 2026-09-26 06:00 |  | Sribalaje | Sribalaje, Ganesh
31 | Configure Integration broker Framework | 0:40 | 2026-09-26 06:00 | 2026-09-26 06:40
32 | Open Search configuration on SDHP92,SDFP92 & SDPP91 | 2:00 | 2026-09-26 06:40 | 2026-09-26 08:40 |  | Sribalaje | Sribalaje, Ganesh
33 | REN Server Configuration on SDFP92 | 0:40 | 2026-09-26 08:40 | 2026-09-26 09:20 |  | Sribalaje | Sribalaje, Ganesh
34 | Update the mSUPLRedirectURL & signout on SDFP92SI & SDFP92SISSO(PROD_SUPPLIER & SUPPLIER_SSO) | 0:10 | 2026-09-26 09:20 | 2026-09-26 09:30 |  | Sribalaje | Sribalaje, Ganesh
35 | Run Sample Process on all servers(PSUNX/PSUNX2/PSNT) and ensure it is successful and posted | 0:30 | 2026-09-26 09:30 | 2026-09-26 10:00 |  | Sribalaje | Sribalaje, Ganesh
36 | Bounce with clear cache on Web/App/Process scheduler servers | 0:10 | 2026-09-26 10:00 | 2026-09-26 10:10 |  | Sergey | Prakash/Ravi
37 | Create Production DB restore point before Technical tasks | 0:30 | 2026-09-26 10:10 | 2026-09-26 10:40 |  | Sribalaje | Sribalaje, Ganesh | Does not include Search and REN Configuration.
38 | Ensure Indexes are dropped by DBA-PS_CHARTFIELD1_TBL | 0:00 | 2026-09-26 10:40 | 2026-09-26 10:40 |  | Sergey | Prakash/Ravi
39 | Ensure DBLINKS are working as expected | 0:00 | 2026-09-26 10:40 | 2026-09-26 10:40 |  | Sribalaje | Sribalaje, Ganesh
40 | Ensure PS_FILEDIR Environment Variable has been set on PSUNX & D:\psoft\PSFILEDIR on PSNT | 0:00 | 2026-09-26 10:40 | 2026-09-26 10:40 |  | Sribalaje | Sribalaje, Ganesh
41 | Ensure Origin IP Address console changes works as expected | 0:00 | 2026-09-26 10:40 | 2026-09-26 10:40 |  | Sribalaje | Sribalaje, Ganesh
42 | Test BYPASS URL on Employee Portal,HCM & FSCM | 0:00 | 2026-09-26 10:40 | 2026-09-26 10:40 |  | Sribalaje | Sribalaje, Ganesh
43 | Test CG, SDFP92SI | 0:00 | 2026-09-26 10:40 | 2026-09-26 10:40 |  | Sribalaje | Sribalaje, Ganesh
57 | PIA Validation -Complete IVT | 3:00 | 2026-09-26 10:40 | 2026-09-26 13:40 |  | Sri Balaje | Sribalaje, Ganesh
58 | Create Production DB Restore points | 0:20 | 2026-09-26 10:40 | 2026-09-26 11:00 |  | Sergey | Prakash/Ravi
59 | COMM: CherryRoad Technical Validation complete | 0:00 | 2026-09-26 11:00 | 2026-09-26 11:00 |  | Sribalaje | Sribalaje, Ganesh
60 | SDCOE Technical tasks - Steve | 4:00 | 2026-09-26 11:00 | 2026-09-26 15:00
61 | Break | 6:30 | 2026-09-26 11:00 | 2026-09-26 17:30
62 | Bounce and clear cache after SDCOE confirmation | 0:20 | 2026-09-26 17:30 | 2026-09-26 17:50 |  | Sribalaje | Sribalaje, Ganesh
63 | Test OKTA URL(Employee Portal & ESS) including other Production URLs | 0:10 | 2026-09-26 17:50 | 2026-09-26 18:00
64 | Testing and validation by SDCOE Functional and Business stake holders (Smoke Test) | 3:00 | #REF! | #REF! |  |  | SDCOE Team
65 | Go/No Go Decision | 1:00 | #REF! | #REF!
| Post Go Live |  | #REF! | #REF!
67 | COMM: Update Core Team Go Live email String: It's a "Go" Decision. Begin Post Go Live tasks. | 0:00 | #REF! | #REF! |  | Sribalaje | Sribalaje, Ganesh
Incremental Backup Production Databases(SDHP92,SDFP92 & SDPP91)
68 | Unlock remaining end-users locked for Upgrade | 0:10 | #REF! | #REF! |  | Sribalaje | Sribalaje, Ganesh
69 | Release Hold Jobs | 0:30 | #REF! | #REF! |  | Doug | Doug
70 | COMM: Communicate Go Live and release environment to Users. Delete browser cache | 0:10 | #REF! | #REF! |  |  | SDCOE Team
71 | Enable Scheduled backups | 1:00 | #REF! | #REF! |  | Sergey | Prakash/Ravi
Formulas:
End = [Start]+[Dur HR:MM]
End = D44+[Dur HR:MM]
Start = [Start, row above]
Start = [End, row above]

## PIA Validation
PIA Validation | Status | Notes | Owner | Reference
Integration Broker configuration-Gateways, Service Configuration |  |  | Sribalaje
Activate the Domain and configuration status |  |  | Sribalaje
Ensure Nodes on Unified navigation workcenter |  |  | Sribalaje
Ensure Tools release are updated on the Nodes |  |  | Sribalaje
Ensure Fav, Recent Pages and unified navigation is working |  |  | Sribalaje
Ensure Time Zone on system process request |  |  | Sribalaje
Sample Process Test(AE,SQR & CBL) |  |  | Sribalaje
Ren configurtaion and Test |  |  | Sribalaje
Report Node Posting Validations |  |  | Sribalaje
Remote Cobol Test |  |  | Sribalaje
Open Search testing on all Pillars |  |  | Sribalaje
Kibana tesing on all Pillars |  |  | Sribalaje
RTI Configuration and testing
Query to excel test |  |  | Sribalaje
Signout URL test |  |  | Sribalaje
Copy new sqr into new PSNT(NJ-SDP-PSNT1) |  |  | Sribalaje
ESS Login URL Testing |  |  | Sribalaje
Production SSO Internal URL testing |  |  | Sribalaje
Production SSO External URL testing |  |  | Sribalaje
Front Page Logo Check |  |  | Sribalaje
Perform complete IVT |  |  | Sribalaje
Ensure Forgot my password is working on Internal & External
Ensure Indexes are dropped by DBA-PS_CHARTFIELD1_TBL
Ensure DBLINKS are working as expected
Ensure PS_FILEDIR Environment Variable has been set on PSUNX & D:\psoft\PSFILEDIR on PSNT
Ensure Origin IP Address console changes works as expected
Test BYPASS URL on Employee Portal,HCM & FSCM
Test CG, SDFP92SI
Post-Upgrade Technical Tasks

## Lockout_Scripts
OPRID ID LOCK
Before running take export of PSOPRDEFN
Before locking ensure ACCTLOCK should not have 2 for any other ID's
For Locking
SELECT DECODE(ACCTLOCK, 0, 'OPEN', 1, 'LOCKED', 'OTHER') ACCT_LOCK, COUNT(*) CNT FROM PSOPRDEFN GROUP BY ACCTLOCK;
update PSOPRDEFN set ACCTLOCK=2 where ACCTLOCK=0 and OPRID not in ('PSADMIN','ANONYMOUS','APPSRVR','IBADMIN','PTWEBSERVER','GUEST','GUEST2','FORGOTPASSWORD','M_MONITOR','RECRUIT_GUEST','FMPINT','SUPPLIER','SMURUGESAN','AGANESH','MMURUGAVEL','643135','601300','607809','634951','646827','600732','638073','618061','302536','623049','646471');
For Unlocking:
UPDATE PSOPRDEFN SET ACCTLOCK=0 WHERE ACCTLOCK=2
PROCESS ON-HOLD
UPDATE PSPRCSRQST SET RUNSTATUS=4 WHERE RUNSTATUS=5
UPDATE PSPRCSQUE SET RUNSTATUS=4 WHERE RUNSTATUS=5
Process Release from hold
UPDATE PSPRCSRQST SET RUNSTATUS=5 WHERE RUNSTATUS=4
UPDATE PSPRCSQUE SET RUNSTATUS=5 WHERE RUNSTATUS=4
Export PSOPRDEFN Script:
SET LOG D:\Tools_Upgrade_859\PSOPRDEFN_SDHP92.LOG;
SET OUTPUT D:\Tools_Upgrade_859\PSOPRDEFN_SDHP92.dat;
EXPORT PSOPRDEFN;
SET LOG D:\Tools_Upgrade_859\PSOPRDEFN_SDFP92.LOG;
SET OUTPUT D:\Tools_Upgrade_859\PSOPRDEFN_SDFP92.dat;
EXPORT PSOPRDEFN;
SET LOG D:\Tools_Upgrade_859\PSOPRDEFN_SDPP91.LOG;
SET OUTPUT D:\Tools_Upgrade_859\PSOPRDEFN_SDPP91.dat;
EXPORT PSOPRDEFN;
QUERY TO EXCEL:
HCM – D99_ACTIVE_EARNINGS
PoRTAL – M_USER_PASSWORD_EXPIRES/M_USER_LAST_LOGIN_DATE
FIN – AMDE4001_QUANTITY_COST_SUB
select OPRID,LASTPSWDCHANGE,ACCTLOCK,LASTUPDDTTM from psoprdefn where OPRID in('PSADMIN','ANONYMOUS','APPSRVR','IBADMIN','PTWEBSERVER','GUEST','GUEST2','FORGOTPASSWORD','M_MONITOR','RECRUIT_GUEST','FMPINT','SUPPLIER','GUESTSSO');
update PSOPRDEFN set LASTPSWDCHANGE ='31-DEC-2050' where OPRID in ('PSAPPS','PS','PTWEBSERVER','APPSRVR','ANONYMOUS','IBADMIN');

## Rollback Plan
# | City of San Jose Upgrade Rollback Plan | Dur HR:MM | Start | End | Status | Lead | Team | Comments
| Production Control before Upgrade Activities |  | #REF! | #REF! |  |  |  | Assumes start date time of Go/No Go call.
| COMM: Rollback begins | 0:00 | #REF! | #REF! | Not Started | CSJ Team | CSJ Team
1 | Hold all scheduled processes before shutdown of upgraded Production | 0:15 | #REF! | #REF! | Not Started | Ashley | CSJ Team | Processes send out bound files. Reprocess Neogov file.
2 | Shutdown App/Web/Process schedulers on New PTools | 1:00 | #REF! | #REF! | Not Started | Sribalaje | Mathi, Rick
3 | Restore databases to restore points in production (if we face issues we may need to restore full database from backup) | 1:00 | #REF! | #REF! | Not Started | Sri | Mathi
4 | Restore databases to restore points in DR (if we face issues we may need to rebuild DR using fresh backup) | 0:30 | #REF! | #REF! | Not Started | Ashley | CSJ Team
6 | Bring up App/Web/Process schedulers on old release | 0:10 | #REF! | #REF! | Not Started | Sribalaje | Mathi, Rick
7 | Validate Production, ESS,CG,Supplier Portal & SSO instances | 0:15 | #REF! | #REF! | Not Started | Sribalaje | Mathi, Rick
8 | Validate restored application | 0:15 | #REF! | #REF! | Not Started | Ashley | CSJ Team
| COMM: Rollback Successful | 0:00 | #REF! | #REF! | Not Started | CSJ Team | CSJ Team

## INTG Changes (hidden)
# | Integration changes | Status | Owner | Change | Target | Notes
Old sheet. See OL8 PLAN.
1 | Provide INPAS 9.2 OL8 link | Not Started | Lori |  |  | https://uatappoel27.cloud.inprs.in.gov:8091/psp/ermpasu1/?cmd=login
2 | Unlock QA users & Josh in INPAS 9.2 | Not Started | Brian J.
2.1 | Provide INPAS Oracle Database connection info | Not Started | Brian
3 | Provide ERM OL8 link | Not Started | Jamie
4 | Provide ERM OL8 db properties | Not Started | Abundo |  |  | DB Properties = DESCRIPTION = (ADDRESS = (PROTOCOL = TCP)(HOST = sitoraoel24.cloud.inprs.in.gov)(PORT = 1678)) (CONNECT_DATA = (SERVER = DEDICATED) (SERVICE_NAME = ERMPASS1)))
5 | Change BPM pointers to OL8 INPAS/ERM | Not Started | Bill S. | BPM | INPAS/ERM
6 | Change BPM Pointers to OL8 INPAS server | Not Started | Bill S. | BPM | INPAS
7 | Connect EBS OL7 to OL8 INPAS | Not Started | Kurt | EBS | INPAS
9 | Deploy new code for OL8 ERM | Not Started | Suresh/Yekasi | ERM
10 | Deploy new code for OL8 ERM_Scheduler | Not Started | Suresh/Yekasi | ERM
8 | Change Pointers on OL8 ERM | Not Started | Jyostna | ERM
10 | Change pointers in ERM scheduler for INPAS web service | Not Started | Jyostna/Matt | ERM | INPAS | ERM.25.05 release created in SN RLSE0012222 – ERM & ERM Scheduler
11 | Change OL8 ERM pointers to Ol7 EBS | Not Started | Suresh | ERM | EBS
12 | Change OL8 ERM pointers to Ol7 Looker | Not Started | Basha | ERM | Looker | *Beth follow up with Tim and Basha
13 | Change OL8 ERM pointers to Ol7 Atrium | Not Started | Suresh/Jyostna | ERM | Atrium
14 | Configure ITR (Gitlab) API used by RAC | Not Started | Bill S. | ITR | RAC | tbd. (still pending Bill S-work with Josh P)
15 | Create new OL7 Jenkins pipeline ERM and ERM_scheduler | Not Started | Venkata | Jenkins | ERM
22 | Sit Perf credentials Jenkins Prod ofr OL8 | Not Started | Venkata/Abundo | Jenkins
16 | Deploy MuleSoft FileNet functionality for OL8 INPAS | Not Started | Brian P./Dirk | MuleSoft | INPAS
17 | Deploy INPAS FileNet Code | Not Started | Jay | INPAS | MuleSoft | Part of upgrade Go Live
18 | Connect OSB to OL8 INPAS/ERM | Not Started | Bill S. | OSB | INPAS/ERM
19 | Create OL8 ERM db keys for OL7 Rundeck containers Jobs | Not Started | Abundo | ERM | Rundeck | Dbkeys and Node
20 | Create Rundeck Nodes | Not Started | Suresh | Rundeck |  | –(Suresh/ERM dev team still pending)no nightly jobs will be processed )
21 | Create Db connections string for OL8 Rundeck Job | Not Started | Abundo | Rundeck |  | Connection Strings
| Load Mulesoft certificates into PeopleSoft digital certificate table |  | Brian | MuleSoft
| Update Integration properties file to bypass resolving the MuleSoft server names to IP addresses |  | Brian | MuleSoft

## Svr Access (hidden)
Access these locations
Defect
Old. DNE | \\nycfas03\sftp\stsdata\nysesdc( | B2G Contract interface abends at step Filepath ESDBYGPINT | AAAA-0004-2438 | Process uses URL definition ESD_B2G_INT to determine the FTP server
Prod | nj-esd-fnp-ap01
Hostname | nj-esd-fnp-ap01 | DC NP server
ESD dev | vFMSAPPD | non-prod server at ESD
Notes:
| AZE-ANF-e968.empire.internal |  |  | We should not be writing to this server from the DC
| \\AZE-ANF-e968.empire.internal\AZE-ANF-STS01\STSData | Bank File server